## Slide 1
DB Fahrzeuginstandhaltung | New Cottbus Plant
MACHINE DATA ACQUISITION (MDA)
Strategic Timeline
& Rollout Plan
Section 5: Milestones & Tools · June 2027 SoP
2nd March 2026
Notes: This presentation covers the MDA strategic timeline and rollout plan for the new DB FZI Cottbus plant, targeting a June 2027 Start of Production (SoP). The plan follows a Stage-Gate® methodology and tiered system prioritisation.
References:
PMI. (2021). PMBOK® Guide — A guide to the project management body of knowledge (7th ed.). Project Management Institute.
Cooper, R. G. (1990). Stage-gate systems: A new tool for managing new products. Business Horizons, 33(3), 44–54.

## Slide 2
AGENDA
What we
will cover
01
Hybrid Rollout Strategy
02
System Prioritisation Tiers
03
Four-Phase Timeline to SoP
04
Key Tools & Methods
05
MDA Blueprint & Cross-Plant Rollout
Notes: The agenda covers five key areas: hybrid rollout strategy, system prioritisation tiers, the four-phase timeline to SoP, key tools & methods, and the MDA Blueprint for cross-plant rollout.
References:
Kerzner, H. (2022). Project management: A systems approach to planning, scheduling, and controlling (13th ed.). Wiley.
Cooper, R. G. (1990). Stage-gate systems: A new tool for managing new products. Business Horizons, 33(3), 44–54.

## Slide 3
ROLLOUT STRATEGY
Hybrid Sequencing Logic
Why a hybrid approach? A system-type approach ignores construction sequencing. A section-only approach misses economies of scale. The hybrid model balances both.
PRIMARY CRITERION
1
System Criticality
High-value, safety-critical, and audit-required systems connect first to maximise early value and compliance.
SECONDARY CRITERION
2
Building Section Readiness
Systems in completed plant sections are connected first to avoid rework and access conflicts.
TERTIARY CRITERION
3
Interface Type Clustering
Systems sharing the same protocol (e.g. OPC-UA) are bundled together to reuse connectors and cut integration costs.
Notes: The hybrid sequencing logic combines three criteria: system criticality (safety-critical first), building section readiness (completed areas first), and interface type clustering (OPC-UA bundles). This avoids the limitations of a purely system-type or section-only approach.
References:
Cooper, R. G. (1990). Stage-gate systems: A new tool for managing new products. Business Horizons, 33(3), 44–54, p. 47.
Kerzner, H. (2022). Project management: A systems approach to planning, scheduling, and controlling (13th ed.). Wiley, pp. 108–133.
Turner, J. R., & Cochrane, R. A. (1993). Goals-and-methods matrix: Coping with projects with ill-defined goals and/or methods of achieving them. International Journal of Project Management, 11(2), 93–102.

## Slide 4
SYSTEM PRIORITISATION
Three-Tier Categorisation of 100 Systems
Tier 1
HIGH PRIORITY
Wheel lathes · Lifting systems · Brake test rigs · Washing plants
Safety-critical; generate audit-required data; highest downtime cost impact.
~15–20 systems
Phase 1 — Pilot
Tier 2
MEDIUM PRIORITY
CNC machines · Welding stations · Compressors · Conveyor systems
High energy & material consumption; significant OEE impact.
~50 systems
Phase 2 — Scale-Up
Tier 3
STANDARD
General workshop equipment · Measurement tools · Auxiliary systems
Relevant for completeness; lower operational criticality.
~30–35 systems
Phase 2 / Phase 3
Notes: The 100 systems are categorised into three tiers based on operational criticality. Tier 1 (~15–20 systems) covers safety-critical assets such as wheel lathes, lifting systems, and brake test rigs. Tier 2 (~50 systems) addresses OEE-impact assets. Tier 3 (~30–35 systems) covers standard workshop equipment. This prioritisation follows Cooper's (1990) recommendation to sequence deliverables by value and risk.
References:
Cooper, R. G. (1990). Stage-gate systems: A new tool for managing new products. Business Horizons, 33(3), 44–54.
PMI. (2021). PMBOK® Guide (7th ed.). Project Management Institute, p. 245 — definition of milestones.
Turner, J. R., & Cochrane, R. A. (1993). Goals-and-methods matrix. International Journal of Project Management, 11(2), 93–102.

## Slide 5
ROLLOUT GANTT CHART
Tier-by-Tier Schedule: Q1 2026 → June 2027 SoP
Jan
2026
Feb
Mar
Apr
May
Jun
Jul
Aug
Sep
Oct
Nov
Dec
Jan
2027
Feb
Mar
Apr
May
Jun
SoP
PHASE OVERVIEW
Ph 0: Foundation
Ph 1: Pilot
Ph 2: Scale-Up
TIER 1 — SAFETY-CRITICAL (~15–20 systems)
Wheel Lathes
2–3 units
Connect
Live
Lifting Systems
4–5 units
Connect
Live
Brake Test Rigs
3–4 units
Connect
Live
Washing Plants
2–3 units
Connect
TIER 2 — OEE IMPACT (~50 systems)
CNC Machines
~12 units
Connect
Live
Welding Stations
~15 units
Connect
Compressors
~10 units
Connect
Conveyor Systems
~13 units
Connect
TIER 3 — STANDARD (~30–35 systems)
Workshop Equip.
~20 units
Connect
Aux. Systems
~15 units
Connect
Tier 1 Connect
Tier 1 Live
Tier 2 Connect
Tier 2 Live
Tier 3 Connect
Tier 3 Live
Notes: This Gantt chart shows the tier-by-tier rollout schedule from Q1 2026 to the June 2027 SoP. Phase 0 (Foundation) establishes architecture and vendor contracts. Phase 1 (Pilot) connects Tier 1 safety-critical systems. Phase 2 (Scale-Up) rolls out Tier 2 and Tier 3 systems. Phase 3 (SoP Ready) completes acceptance and handover. A 4–6 week buffer is embedded at each phase transition to absorb construction or vendor delays.
References:
Cooper, R. G. (1990). Stage-gate systems: A new tool for managing new products. Business Horizons, 33(3), 44–54, p. 47 — phase-gate scheduling.
Kerzner, H. (2022). Project management (13th ed.). Wiley, p. 133 — CPM scheduling standard for hard deadlines.
Cooper, R. G. (2008). The Stage-Gate® idea-to-launch process — Update, what's new, and NexGen systems. Journal of Product Innovation Management, 25(3), 213–232.

## Slide 6
FOUR-PHASE TIMELINE
Road to June 2027 SoP
PHASE 0
Foundation
Q1–Q2 2026
▸ Finalize MDA architecture & data standards
▸ System inventory & interface analysis (100 systems)
▸ Works Council pre-alignment on data levels 1–4
▸ Vendor contract framework established
RACI · Interface Catalogue · Risk Register
PHASE 1
Pilot
Q3–Q4 2026
▸ Connect ~15–20 Tier 1 systems (wheel lathes, test rigs)
▸ MDA Level 1: automated data collection live
▸ OEE baseline measurements established
▸ Blueprint v1 drafted
IoT Middleware · OPC-UA Adapters · Grafana
PHASE 2
Scale-Up
Q1–Q2 2027
▸ Roll out remaining ~80 systems by building section
▸ MDA Level 2: real-time transparency activated
▸ Integration tests — SAP PM, MES streams
▸ Works Council sign-off on data usage
Jira · MES/SAP-PM Connectors · Test Protocols
PHASE 3
SoP Ready
May–Jun 2027
▸ Full acceptance testing — all 100 systems
▸ Live OEE dashboard for public presentation
▸ Staff training & operational handover to DB FZI
▸ Blueprint v2 — cross-plant guide — published
KPI Dashboard · Acceptance Suite · Lessons Learned
⚑ 4–6 week buffer embedded at each phase transition to absorb construction or vendor delays
Notes: The four phases follow Cooper's (1990, 2008) Stage-Gate® model: each phase ends with a management decision gate before the next phase is authorised. Phase 0 finalises the MDA architecture, Phase 1 connects pilot Tier 1 systems, Phase 2 scales to remaining ~80 systems, and Phase 3 delivers full acceptance and SoP handover.
References:
Cooper, R. G. (1990). Stage-gate systems: A new tool for managing new products. Business Horizons, 33(3), 44–54.
Cooper, R. G. (2008). The Stage-Gate® idea-to-launch process. Journal of Product Innovation Management, 25(3), 213–232, p. 215.
PMI. (2021). PMBOK® Guide (7th ed.). Project Management Institute — milestone-based project planning.
Andersen, E. S., Grude, K. V., & Haug, T. (2009). Goal directed project management (4th ed.). Kogan Page — participatory milestone planning.

## Slide 7
KEY TOOLS & METHODS
Project Management & Technical Infrastructure
PROJECT MANAGEMENT
TECHNICAL INFRASTRUCTURE
MS Project / Jira
Master project plan tracking 100 system connections across all phases, with dependencies mapped to building section access dates.
RACI Matrix
Defines responsibilities between DB FZI (requirements), DB Systel (IT delivery), and vendors (system interfaces).
Risk Register
Maintained from Phase 0, reviewed bi-weekly, escalated to programme level if red-rated.
Interface Catalogue
Living document: all 100 systems, manufacturers, protocols (OPC-UA, Profinet, Modbus), and connection status.
IoT Middleware / Edge Gateways
Protocol-agnostic middleware (Azure IoT Hub, Siemens MindSphere, Node-RED) handles heterogeneous interfaces without bespoke development.
OPC-UA Adapters
Standardised communication layer — significantly reduces integration effort when vendors support this protocol.
OEE Dashboard (Grafana / Power BI)
Real-time visualisation of availability, performance & quality. Live by Phase 1 for pilot systems; full plant view by SoP.
MES / SAP-PM Connector
Integration between MDA data streams and maintenance management systems for workflow triggers and audit logging.
Notes: The key tools split into project management (MS Project/Jira, RACI Matrix, Risk Register, Interface Catalogue) and technical infrastructure (IoT Middleware, OPC-UA Adapters, OEE Dashboard, MES/SAP-PM Connectors). MS Project with CPM is the scheduling standard for projects with hard external deadlines (Kerzner, 2022, p. 133).
References:
Kerzner, H. (2022). Project management: A systems approach to planning, scheduling, and controlling (13th ed.). Wiley, p. 133.
PMI. (2021). PMBOK® Guide (7th ed.). Project Management Institute, p. 160 — RACI framework.
Davis, S. M., & Lawrence, P. R. (1977). Matrix. Addison-Wesley — matrix governance and role clarity.

## Slide 8
CROSS-PLANT STRATEGY
MDA Blueprint — Transferable Knowledge System
Starting Phase 1, all technical and organisational learnings are captured in a structured Blueprint that enables future cross-plant rollout.
Interface Connector Specs
Reusable connector specifications per protocol type (OPC-UA, Modbus, Profinet), applicable to any DB FZI plant.
Data Model Standards
Consistent KPI calculation logic for OEE, availability, and energy — enabling cross-plant comparability.
Vendor Templates
Standard MDA procurement clauses mandating OPC-UA interfaces — reducing future integration costs plant-wide.
Works Council Playbook
Engagement checklist and communication templates for navigating data-level sensitivities at other plants.
Blueprint v1 → End of Phase 1 (Q4 2026) Blueprint v2 → SoP (June 2027) — Definitive cross-plant guide
Notes: The MDA Blueprint captures all technical and organisational learnings from Cottbus in a structured, transferable format. Blueprint v1 is delivered at the end of Phase 1 (Q4 2026), and Blueprint v2 — the definitive cross-plant guide — at SoP (June 2027). Components include interface connector specs, data model standards, vendor templates, and a Works Council playbook.
References:
Cooper, R. G. (2008). The Stage-Gate® idea-to-launch process. Journal of Product Innovation Management, 25(3), 213–232 — knowledge capture across gates.
Kerzner, H. (2022). Project management (13th ed.). Wiley — lessons learned and knowledge management.
PMI. (2021). PMBOK® Guide (7th ed.). Project Management Institute — organisational process assets.

## Slide 9
KEY TAKEAWAYS
Summary
1
Hybrid sequencing combines system criticality, building section readiness, and interface clustering for maximum efficiency.
2
Four clear phases provide buffer-protected milestones from Q1 2026 through the June 2027 SoP.
3
Tiered prioritisation ensures Tier 1 safety-critical systems deliver value in Phase 1 before full scale-up.
4
MDA Blueprint transforms Cottbus learnings into a reusable asset for all future DB FZI plant rollouts.
DB FZI — MDA Project · New Cottbus Plant · Target: June 2027 SoP
Notes: Four key takeaways: (1) Hybrid sequencing combines criticality, readiness, and interface clustering. (2) Four buffer-protected phases lead to the June 2027 SoP. (3) Tiered prioritisation ensures Tier 1 safety-critical systems deliver value first. (4) The MDA Blueprint transforms Cottbus learnings into reusable assets for all future DB FZI plants.
References:
PMI. (2021). PMBOK® Guide — A guide to the project management body of knowledge (7th ed.). Project Management Institute.
Kerzner, H. (2022). Project management: A systems approach to planning, scheduling, and controlling (13th ed.). Wiley.
Cooper, R. G. (1990). Stage-gate systems: A new tool for managing new products. Business Horizons, 33(3), 44–54.
Cooper, R. G. (2008). The Stage-Gate® idea-to-launch process — Update, what's new, and NexGen systems. Journal of Product Innovation Management, 25(3), 213–232.
Turner, J. R., & Cochrane, R. A. (1993). Goals-and-methods matrix. International Journal of Project Management, 11(2), 93–102.
Galbraith, J. R. (1971). Matrix organization designs. Business Horizons, 14(1), 29–40.
Davis, S. M., & Lawrence, P. R. (1977). Matrix. Addison-Wesley.
Andersen, E. S., Grude, K. V., & Haug, T. (2009). Goal directed project management (4th ed.). Kogan Page.

## Slide 10
APA REFERENCES
Full Reference List
[1] PMI. (2021). PMBOK® Guide — A guide to the project management body of knowledge (7th ed.). Project Management Institute.
[2] Kerzner, H. (2022). Project management: A systems approach to planning, scheduling, and controlling (13th ed.). Wiley.
[4] Galbraith, J. R. (1971). Matrix organization designs: How to combine functional and project forms. Business Horizons, 14(1), 29–40.
[5] Davis, S. M., & Lawrence, P. R. (1977). Matrix. Addison-Wesley.
[7] Turner, J. R., & Cochrane, R. A. (1993). Goals-and-methods matrix: Coping with projects with ill-defined goals and/or methods of achieving them. International Journal of Project Management, 11(2), 93–102.
[8] Andersen, E. S., Grude, K. V., & Haug, T. (2009). Goal directed project management (4th ed.). Kogan Page. Cited in Miranda, E. (2019). Milestone planning. PM World Journal, VIII(XI).
[9] Cooper, R. G. (1990). Stage-gate systems: A new tool for managing new products. Business Horizons, 33(3), 44–54.
[10] Cooper, R. G. (2008). The Stage-Gate® idea-to-launch process — Update, what's new, and NexGen systems. Journal of Product Innovation Management, 25(3), 213–232.
DB FZI — MDA Project · New Cottbus Plant · Target: June 2027 SoP