## Slide 1
DB Fahrzeuginstandhaltung | New Cottbus Plant
MACHINE DATA ACQUISITION (MDA)
Strategic Timeline
& Rollout Plan
Section 5: Milestones & Tools · June 2027 SoP
2nd March 2026

## Slide 2
AGENDA
What we
will cover
01
Hybrid Rollout Strategy
02
System Prioritisation Tiers
03
Four-Phase Timeline to SoP
04
Key Tools & Methods
05
MDA Blueprint & Cross-Plant Rollout

## Slide 3
ROLLOUT STRATEGY
Hybrid Sequencing Logic
Why a hybrid approach? A system-type approach ignores construction sequencing. A section-only approach misses economies of scale. The hybrid model balances both.
PRIMARY CRITERION
1
System Criticality
High-value, safety-critical, and audit-required systems connect first to maximise early value and compliance.
SECONDARY CRITERION
2
Building Section Readiness
Systems in completed plant sections are connected first to avoid rework and access conflicts.
TERTIARY CRITERION
3
Interface Type Clustering
Systems sharing the same protocol (e.g. OPC-UA) are bundled together to reuse connectors and cut integration costs.

## Slide 4
SYSTEM PRIORITISATION
Three-Tier Categorisation of 100 Systems
Tier 1
HIGH PRIORITY
Wheel lathes · Lifting systems · Brake test rigs · Washing plants
Safety-critical; generate audit-required data; highest downtime cost impact.
~15–20 systems
Phase 1 — Pilot
Tier 2
MEDIUM PRIORITY
CNC machines · Welding stations · Compressors · Conveyor systems
High energy & material consumption; significant OEE impact.
~50 systems
Phase 2 — Scale-Up
Tier 3
STANDARD
General workshop equipment · Measurement tools · Auxiliary systems
Relevant for completeness; lower operational criticality.
~30–35 systems
Phase 2 / Phase 3

## Slide 5
ROLLOUT GANTT CHART
Tier-by-Tier Schedule: Q1 2026 → June 2027 SoP
Jan
2026
Feb
Mar
Apr
May
Jun
Jul
Aug
Sep
Oct
Nov
Dec
Jan
2027
Feb
Mar
Apr
May
Jun
SoP
PHASE OVERVIEW
Ph 0: Foundation
Ph 1: Pilot
Ph 2: Scale-Up
TIER 1 — SAFETY-CRITICAL (~15–20 systems)
Wheel Lathes
2–3 units
Connect
Live
Lifting Systems
4–5 units
Connect
Live
Brake Test Rigs
3–4 units
Connect
Live
Washing Plants
2–3 units
Connect
TIER 2 — OEE IMPACT (~50 systems)
CNC Machines
~12 units
Connect
Live
Welding Stations
~15 units
Connect
Compressors
~10 units
Connect
Conveyor Systems
~13 units
Connect
TIER 3 — STANDARD (~30–35 systems)
Workshop Equip.
~20 units
Connect
Aux. Systems
~15 units
Connect
Tier 1 Connect
Tier 1 Live
Tier 2 Connect
Tier 2 Live
Tier 3 Connect
Tier 3 Live

## Slide 6
FOUR-PHASE TIMELINE
Road to June 2027 SoP
PHASE 0
Foundation
Q1–Q2 2026
▸ Finalize MDA architecture & data standards
▸ System inventory & interface analysis (100 systems)
▸ Works Council pre-alignment on data levels 1–4
▸ Vendor contract framework established
RACI · Interface Catalogue · Risk Register
PHASE 1
Pilot
Q3–Q4 2026
▸ Connect ~15–20 Tier 1 systems (wheel lathes, test rigs)
▸ MDA Level 1: automated data collection live
▸ OEE baseline measurements established
▸ Blueprint v1 drafted
IoT Middleware · OPC-UA Adapters · Grafana
PHASE 2
Scale-Up
Q1–Q2 2027
▸ Roll out remaining ~80 systems by building section
▸ MDA Level 2: real-time transparency activated
▸ Integration tests — SAP PM, MES streams
▸ Works Council sign-off on data usage
Jira · MES/SAP-PM Connectors · Test Protocols
PHASE 3
SoP Ready
May–Jun 2027
▸ Full acceptance testing — all 100 systems
▸ Live OEE dashboard for public presentation
▸ Staff training & operational handover to DB FZI
▸ Blueprint v2 — cross-plant guide — published
KPI Dashboard · Acceptance Suite · Lessons Learned
⚑ 4–6 week buffer embedded at each phase transition to absorb construction or vendor delays

## Slide 7
KEY TOOLS & METHODS
Project Management & Technical Infrastructure
PROJECT MANAGEMENT
TECHNICAL INFRASTRUCTURE
MS Project / Jira
Master project plan tracking 100 system connections across all phases, with dependencies mapped to building section access dates.
RACI Matrix
Defines responsibilities between DB FZI (requirements), DB Systel (IT delivery), and vendors (system interfaces).
Risk Register
Maintained from Phase 0, reviewed bi-weekly, escalated to programme level if red-rated.
Interface Catalogue
Living document: all 100 systems, manufacturers, protocols (OPC-UA, Profinet, Modbus), and connection status.
IoT Middleware / Edge Gateways
Protocol-agnostic middleware (Azure IoT Hub, Siemens MindSphere, Node-RED) handles heterogeneous interfaces without bespoke development.
OPC-UA Adapters
Standardised communication layer — significantly reduces integration effort when vendors support this protocol.
OEE Dashboard (Grafana / Power BI)
Real-time visualisation of availability, performance & quality. Live by Phase 1 for pilot systems; full plant view by SoP.
MES / SAP-PM Connector
Integration between MDA data streams and maintenance management systems for workflow triggers and audit logging.

## Slide 8
CROSS-PLANT STRATEGY
MDA Blueprint — Transferable Knowledge System
Starting Phase 1, all technical and organisational learnings are captured in a structured Blueprint that enables future cross-plant rollout.
Interface Connector Specs
Reusable connector specifications per protocol type (OPC-UA, Modbus, Profinet), applicable to any DB FZI plant.
Data Model Standards
Consistent KPI calculation logic for OEE, availability, and energy — enabling cross-plant comparability.
Vendor Templates
Standard MDA procurement clauses mandating OPC-UA interfaces — reducing future integration costs plant-wide.
Works Council Playbook
Engagement checklist and communication templates for navigating data-level sensitivities at other plants.
Blueprint v1 → End of Phase 1 (Q4 2026) Blueprint v2 → SoP (June 2027) — Definitive cross-plant guide

## Slide 9
KEY TAKEAWAYS
Summary
1
Hybrid sequencing combines system criticality, building section readiness, and interface clustering for maximum efficiency.
2
Four clear phases provide buffer-protected milestones from Q1 2026 through the June 2027 SoP.
3
Tiered prioritisation ensures Tier 1 safety-critical systems deliver value in Phase 1 before full scale-up.
4
MDA Blueprint transforms Cottbus learnings into a reusable asset for all future DB FZI plant rollouts.
DB FZI — MDA Project · New Cottbus Plant · Target: June 2027 SoP