## Slide 1
QUESTIONS 4 & 5
Project Management
Organisation
& Milestones
Academic Framework Applied to the MDA — New Cottbus Plant
PMBOK® · Kerzner · Cooper · Turner & Cochrane
DB FZI — MDA Project · New Cottbus Plant · March 2026

## Slide 2
QUESTION 4 — RECOMMENDED STRUCTURE
Strong Matrix Organisation for the MDA Project
Kerzner (2022, p. 108): Matrix is preferred when (a) interdisciplinary teamwork is required, (b) resources are shared across projects, and (c) one PM must be accountable for delivery. All three apply here.
STEERING COMMITTEE
DB FZI Sponsor · DB Systel Director · Works Council Rep
MDA PROJECT MANAGER
DB Systel · Strong Matrix Authority
Technical Architecture
MDA system design
OPC-UA / protocol standards
Edge gateway config
Vendor integration
Project Integration & PMO
Master schedule & risk register
Reporting to Steering Committee
Change control
Budget tracking
Stakeholder & Compliance
Works Council liaison
DSGVO / BDSG compliance
Staff communication
Operational readiness
[1] PMI (2021). PMBOK® Guide, 7th ed., p. 160 · [2] Kerzner, H. (2022). Project Management, 13th ed., Wiley, p. 108 · [4] Galbraith (1971). Business Horizons, 14(1), 29–40 · [5] Davis & Lawrence (1977). Matrix, Addison-Wesley, p. 131

## Slide 3
QUESTION 4 — GOVERNANCE & RISK
Matrix Risk, RACI Framework & Mitigations
⚠ THE RISK: DUAL REPORTING CONFLICT
The academic literature consistently identifies role ambiguity as the primary weakness of matrix structures. Galbraith (1971) [4] and Davis & Lawrence (1977, p. 134) [5] observe that employees facing conflicting instructions from both a PM and a functional manager experience stress and reduced productivity. In the MDA project: DB Systel engineers working across 50 subprojects may deprioritise MDA tasks in favour of functional department demands.
✓ RACI & MITIGATIONS FOR MDA
Role
Responsible (R)
Accountable (A)
Consulted (C)
Informed (I)
DB FZI PM
MDA deliverables
Scope & budget
DB Systel
Sponsor
DB Systel Eng.
IT integration
DB FZI PM
Vendors
Works Council
Works Council
—
Data usage
DB FZI PM
Steering Cmte
Vendors
OPC-UA connect
Vendor PM
DB Systel
—
1
Escalation Paths
Formal escalation to Steering Committee for resource conflicts — PM authority is backed by governance.
2
Contractual Delineation
Clear DB FZI / DB Systel / Vendor responsibilities defined in the partnership agreement.
3
Bi-weekly Risk Review
RACI reviewed every sprint; red-rated items escalated immediately to programme level.
[4] Galbraith (1971). Business Horizons, 14(1), 29–40 · [5] Davis & Lawrence (1977). Matrix, Addison-Wesley, p. 134 · RACI: Project Management Institute (2021). PMBOK® Guide, 7th ed., p. 160

## Slide 4
QUESTION 5 — ACADEMIC FRAMEWORK
Milestones & Stage-Gate® Model
WHAT IS A MILESTONE?
PMBOK® Guide (7th ed., p. 245):
"A milestone is a significant point or event in a project, programme, or portfolio."
Zero Duration
Milestones mark a state, not an activity — they have no duration.
Kerzner (2022, p. 24) [2]
Outcome State
Turner & Cochrane (1993, p. 94) [7]: Plan around what must be achieved, not how to achieve it.
Participatory
Andersen et al. (2009) [8]: Milestones built with the team increase commitment — critical given Works Council.
STAGE-GATE® MODEL — COOPER (1990, 2008)
"A conceptual and operational road map…dividing the effort into distinct stages separated by management decision gates." — Cooper (1990, p. 44) [9]
Ph 0
Foundation
G0
Ph 1
Pilot
G1
Ph 2
Scale-Up
G2
Ph 3
SoP Ready
SoP
2027
G3
Go/No-Go Authority
Gates require Steering Committee sign-off before next phase is funded. Prevents scope creep across 50 sub-projects. [9]
Deliverable-Based
Phases close only when outputs are achieved ('Interface Catalogue v1 approved'), not when time elapses. [9]
Risk Embedded by Design
Cooper (2008, p. 215): checkpoints "provide for project control and management." Gates surface risks early. [10]
[1] PMI (2021). PMBOK® Guide, 7th ed., p. 245 · [2] Kerzner (2022), p. 24 · [7] Turner & Cochrane (1993). IJPM, 11(2), 93–102 · [8] Andersen et al. (2009) · [9] Cooper (1990). Business Horizons, 33(3), 44–54 · [10] Cooper (2008). JPIM, 25(3), 213–232

## Slide 5
QUESTION 5 — MILESTONES
Six Stage-Gate Milestones: MDA Project
#
Milestone
Gate Criteria
Target
Gatekeepers
M0
Project Initiated
System inventory (100), data standards approved, Works Council informed
End Q1 2026
DB FZI Sponsor · DB Systel PM · Works Council
M1
Pilot Authorised
Interface catalogue v1 approved; RACI signed; OPC-UA vendor contracts in place
End Q2 2026
Steering Committee
M2
MDA Level 1 Live
≥15 Tier 1 systems live; OEE dashboard operational; Blueprint v1 published
End Q4 2026
DB FZI PM · DB Systel Architect
M3
Scale-Up Authorised
No critical defects open; Works Council sign-off on data usage framework
End Q1 2027
Steering Committee
M4
MDA Level 2 Live
100% systems connected; SAP-PM integration tested; training approved
End May 2027
DB FZI Sponsor · DB Systel PM
M5
SoP Handover
Acceptance test signed; staff trained; KPI dashboard live; Blueprint v2 delivered
June 2027 ★
Steering Committee · DB FZI Board
[7] Turner & Cochrane (1993). IJPM, 11(2), 93–102 · [9] Cooper (1990). Business Horizons, 33(3), 44–54, p. 47 · ★ Politically binding SoP date per DB FZI mandate

## Slide 6
ROLLOUT GANTT CHART
Tier-by-Tier Schedule: Q1 2026 → June 2027 SoP
2026
2027
Jan
Feb
Mar
Apr
May
Jun
Jul
Aug
Sep
Oct
Nov
Dec
Jan
Feb
Mar
Apr
May
Jun
Activity
PHASE OVERVIEW
Ph 0: Foundation
Ph 1: Pilot
Ph 2: Scale-Up
Ph 3: SoP Ready
TIER 1 — SAFETY-CRITICAL (~15–20 systems)
Wheel Lathes (2–3)
Connect
Live
Lifting Systems (4–5)
Connect
Live
Brake Test Rigs (3–4)
Connect
Live
TIER 2 — OEE IMPACT (~50 systems)
CNC Machines (~12)
Connect
Live
Welding / Compressors
Connect
Live
TIER 3 — STANDARD (~30–35 systems)
Workshop / Auxiliary
Connect
Live
★ SoP
Ph 0
Ph 1
Ph 2
Ph 3
Connect
Live
Source: DB FZI MDA Project Rollout Plan (2026) · [9] Cooper (1990), p. 47: phase-gate scheduling · 4–6 week buffer embedded at each phase transition

## Slide 7
QUESTION 5 — RECOMMENDED TOOLS
Hybrid Tool Approach: MS Project + Jira + Confluence
Microsoft Project
Executive / Milestone
Gantt chart with CPM for all 6 milestone gate dates
Resource loading & dependency mapping to construction programme
Kerzner (2022, p. 133): CPM standard for projects with hard external deadlines [2]
Audience: Steering Committee, DB FZI Sponsor
Jira Premium
Operational / Sprint
Issue-level tracking of 100 system connection tasks across 3 tiers
Sprint planning & team-based velocity tracking per phase
Advanced Roadmaps integrates with MS Project for single source of truth
Audience: MDA PM, Technical Architecture, PMO workstream
Confluence
Knowledge / Documentation
MDA Blueprint v1 & v2 documentation hub
Gate review minutes, RACI matrices, interface catalogue
Linked to Jira tasks for full decision-to-delivery traceability
Audience: All project participants + Works Council (read access)
[2] Kerzner, H. (2022). Project Management: A Systems Approach, 13th ed. Wiley, p. 133

## Slide 8
QUESTIONS 4 & 5 — INTEGRATED RISK MANAGEMENT
Risk Management Embedded in Organisation & Milestones
Risk management is not a separate workstream — it is embedded in the gate criteria at every milestone and in the RACI at every organisational level.
Q
Layer
Risk
PM Response (Gate / RACI Action)
Q4
Strong Matrix
Role ambiguity & dual reporting conflicts
RACI matrix defines decision rights; escalation path to Steering Committee (Davis & Lawrence, 1977) [5]
Q4
Governance
Decisions contradicted across DB FZI / DB Systel / Vendors
Steering Committee with formal mandate; bi-weekly review; ad-hoc escalation protocol [1]
Q5
Gate M0–M1
Vendor interface surprises — 100 heterogeneous systems
Gate M1 requires OPC-UA vendor contracts signed before Phase 1 authorised; Interface Catalogue v1 [9]
Q5
Gate M2–M3
Works Council escalation on data usage levels
Gate M3 requires Works Council formal sign-off before Scale-Up authorised [8]
Q5
Gate M4–M5
Construction delays blocking system access
4–6 week buffer at each phase transition; Gate M4 held if access not confirmed [2]
Every stage-gate review is simultaneously a risk review — risk management is embedded at both organisational and milestone level.

## Slide 9
CONCLUSION
Key Takeaways
1
Strong Matrix Organisation
The strong matrix with three dedicated workstreams provides the authority, accountability, and resource control required for a 50-subproject, 16-month programme.
2
Stage-Gate® Milestones
Six gate-controlled milestones (M0–M5) enforce deliverable-based progress — no phase advances without Steering Committee sign-off, embedding risk management into governance.
3
Hybrid Rollout — Tier by Tier
Safety-critical Tier 1 systems connect first (Pilot), followed by OEE-impact Tier 2, and standard Tier 3 — balancing compliance, value, and construction sequencing.
4
Risk Is Embedded — Not Separate
RACI, escalation paths, and gate criteria together ensure risk management is structural, not procedural — integrated at every organisational layer and milestone gate.
REFERENCES
[1] PMI. (2021). PMBOK® Guide — A Guide to the Project Management Body of Knowledge, 7th ed. Project Management Institute. pp. 52, 160, 245.
[2] Kerzner, H. (2022). Project Management: A Systems Approach to Planning, Scheduling, and Controlling, 13th ed. Wiley. pp. 24, 108, 133.
[4] Galbraith, J. R. (1971). Matrix Organization Designs: How to Combine Functional and Project Forms. Business Horizons, 14(1), 29–40.
[5] Davis, S. M., & Lawrence, P. R. (1977). Matrix. Addison-Wesley. pp. 131, 134.
[7] Turner, J. R., & Cochrane, R. A. (1993). Goals-and-methods matrix: Coping with projects with ill defined goals and/or methods of achieving them. International Journal of Project Management, 11(2), 93–102.
[8] Miranda, E. (2019). Milestone Planning. PM World Journal, VIII(XI). Citing Andersen, E. S., Grude, K. V., & Haug, T. (2009).
[9] Cooper, R. G. (1990). Stage-gate systems: A new tool for managing new products. Business Horizons, 33(3), 44–54.
[10] Cooper, R. G. (2008). The Stage-Gate® Idea-to-Launch Process — Update, What's New, and NexGen Systems. Journal of Product Innovation Management, 25(3), 213–232.
DB FZI — MDA Project · New Cottbus Plant · Target: June 2027 SoP